**Interaction Dynamics 2nd Meeting**

**Thursday, 28 August 2025 / 2:00-3:30pm / ZT911&Zoom**

**Attendees**

Christina Felfe, Tiare Feuchtner, Wolfgang Gaissmaier, David Garcia, Andrea Hartmann Firnkorn, Raphaela Heesen, Daniel Keim, Daniela Mier, Fridtjof Nussbeck, Jens Pruessner, Giovanni Reina, Harald Schupp, Katinka Wendt, Alexandra Wild, Petra Wirtz

**Minutes**

Title has evolved into “Interaction Dynamics in Human and Machine Communication”.

What’s the overarching goal? Improve impact of digital communication. 🡪 include this in title? 🡪 Moving towards an effective outcome of social interactions

Currently 19 PIs, 5 research areas.

* SFB usually consists of 3 research areas, 4 also possible (e.g., human-human | human-machine | machine-machine; Area C&D could be merged; Area B&C could be merged)
* How can Area C start without the results of Area A&B?

Currently preparing a 3-page document for the Hector Foundation to ask for seed funding.

Proposal process will take up to 24 months and will start after the seed funding decision of the Hector Foundation.

* One meeting in September and one in October to keep the momentum
* Additional meetings per research area meetings might be helpful
* In person meeting where everyone shortly presents their project idea(s)

Preproposal submission in February 2026.

**Action Items**

Everyone to add their research area to the table of the google doc (multiple areas possible).

Everyone to add project ideas to the google doc.

JP to work on updated title and consolidation of research areas.

KW to set up doodles for meetings in September and October.